## Sheet1
Test Scenario Group | Test Case Id | Test Case Description | Test Input | Expected Result | Actual Result | Test Browser | Executed Date | Test Results | Test Comments
Login
Login | Login-1 | Log in with correct username and password as a Test User | username: "valid username", password: "valid password" | redirect to Test User home page | redirect to Test User home page | Chrome | 2019-04-05 | pass
Login | Login-2 | Log in with correct username and invalid password as Test User | username: "valid username", password: "invalid password" | alert "we do not recognize that password" | alert "we do not recognize that username, please register" | Chrome | 2019-04-05 | fail | says invalid username instead of password
Login | Login-3 | Log in with invalid username and valid password as Test User | username: "invalid username", password: "valid password" | alert "we do not recognize that username, please register" | alert "we do not recognize that username, please register" | Chrome | 2019-04-05 | pass
Login | Login-4 | Log in with invalid username and invalid password as Test User | username: "invalid username", password: "invalid password" | alert " we do not recognize that username and password, please register" | alert " we do not recognize that username please register" | Chrome | 2019-04-05 | pass | Just saying username not recognized is fine
Login | Login-5 | Log in with correct username and password as a Admin User | username: "valid username", password: "valid password" | redirect to AdminUser home page | redirect to Admin User home page | Chrome | 2019-04-05 | pass
Login | Login-6 | Log in with correct username and password as a Admin User | username: "valid username", password: "invalid password" | alert "we do not recognize that password" | alert "we do not recognize that username, please register" | Chrome | 2019-04-05 | fail | says invalid username instead of password
Login | Login-7 | Log in with correct username and invalid password as Admin User | username: "invalid username", password: "valid password" | alert "we do not recognize that username, please register" | alert "we do not recognize that username, please register" | Chrome | 2019-04-05 | pass
Login | Login-8 | Log in with invalid username and valid password as Admin User | username: "invalid username", password: "invalid password" | alert " we do not recognize that username and password, please register" | alert " we do not recognize that username please register" | Chrome | 2019-04-05 | pass | Just saying username not recognized is fine
Sign up
Sign up | Sign up-1 | a new user signs up with a new user name, password and retype passwords filled out | username: "new username", password: "new password", retype password: "new password" | go to new userhome page | go to new userhome page | Chrome | 2019-04-05 | pass
Sign up | Sign up-2 | a new user signs up with an existing user name, password and retype passwords filled out | username: "existing username", password: "new password", retype password: "new password" | alert "username already exists" | go to new userhome page | Chrome | 2019-04-05 | fail | say "username already exist" and make a checker to check for existing username
Sign up | Sign up-3 | a new user signs up with an new user name, password and a differnet retype passwords filled out | username: "new username", password: "new password", retype password: "different password" | alert "passwords do not match" | alert "passwords do not match" | Chrome | 2019-04-05 | pass
Sign up | Sign up-4 | a new user signs up with an new user name, an existing password and a retype passwords filled out | username: "new username", password: "existing password", retype password: "existing password" | alert "password already in use" | go to new userhome page | Chrome | 2019-04-05 | fail | make a checker to check for existing password
Sign up | Sign up-5 | a new user signs up with an existing user name, an existing password and a retype passwords filled out | username: "existing username", password: "existing password", retype password: "existing password" | alert "username and password already in use" | go to new userhome page | Chrome | 2019-04-05 | fail | make a checker to check for existing username and password
Redirect to Test
redirect to Test | redirect to Test-1 | Test User clicks on test they have not taken | click test, test user has not taken | redirect to the test page of that test | redirect to the test page of that test | Chrome | 2019-04-08 | pass
redirect to Test | redirect to Test-2 | Test User clicks on test they have taken | click test, test user has taken | redirect to the test result page of that test user with their answer choices and correct answer | redirect to the test result page of that test user with their answer choices and correct answer | Chrome | 2019-04-08 | pass
Take Test
Take Test | Take Test-1 | Test User takes test answers with all correct answers | enters all the correct answers | after Test user submits test they redirected back to their home page with the test name under the completed test and the grade for the exam "100" | after Test user submits test they are redirected back to their home page with the test name under the completed test and the grade for the test "100" | Chrome | 2019-04-08 | pass
Take Test | TakeTest-2 | Test User takes test answers with all correct answers | enters some right answers and wrong answers | after Test user submits test they redirected back to their home page with the test name under the completed test and the grade for the exam "not 100" | after Test user submits test they redirected back to their home page with the test name under the completed test and the grade for the exam "not 100" | Chrome | 2019-04-08 | pass
Take Test | TakeTest-3 | Test User takes test answers with all wrong answers | enters all the wrong ansers | after Test user submits test they redirected back to their home page with the test name under the completed test and the grade for the exam "0" | after Test user submits test they redirected back to their home page with the test name under the completed test and the grade for the exam "not 100" | Chrome | 2019-04-08 | pass
View Test Results
View Test Results | View Test Results-1 | Test User views his test results that show every question, his answer choice and the correct answer choice | clicks on completed test with grade | redirected to test results page with questions, test users answer and the correct answer | redirected to test results page with questions, test users answer and the correct answer | Chrome | 2019-04-08 | pass
Adding test questions
add test Question | add test Question-1 | admin user makes and adds a multiple choice question with question filled and all choices filled and category entered | question and all 4 answer choices and category filled | added to list of questions in question bank | added to questions bank | Chrome | 2019-04-18 | pass
add test Question | add test Question-2 | admin user makes and adds a multiple choice question with question filled and all choices filled and no category entered | question and all 4 answer choices and no category filled | not added to question bank because of no category | added to questions bank | Chrome | 2019-04-18 | fail | fix so that it cannot add to the question bank without a category
add test Question | add test Question-3 | admin user makes and adds a multiple choice question without question filled and choices filled and category filled | no question and all 4 answer choices and category filled | not added to question bank because of no question | not added to questions bank | Chrome | 2019-04-18 | pass
add test Question | add test Question-4 | admin user makes and adds a multiple choice question without question filled, choices filled and no category filled | no question and all 4 answer choices and no category filled | not added to question bank because of no question and no category | not added to questions bank because of no question | Chrome | 2019-04-18 | pass
add test Question | add test Question-5 | admin user makes and adds a multiple choice question with question filled and 3/4 choices filled and category | question and 3/4 answer choices and category filled | added to question bank | not added to question bank | Chrome | 2019-04-18 | fail | fix so admin can put 4 or less choices
add test Question | add test Question-6 | admin user makes and adds a multiple choice question with question filled and 3/4 choices filled and no category entered | question and 3/4 answer choices and no category filled | not added to question bank because of no category | not added to question bank because not all choices filled out | Chrome | 2019-04-18 | pass | fix so admin can put 4 or less choices
add test Question | add test Question-7 | admin user makes and adds a multiple choice question without question filled and 3/4 choices filled and category filled | no question and 3/4 answer choices and category filled | not added to question bank because of no question | not added to question bank because not all choices filled out | Chrome | 2019-04-18 | pass | fix so admin can put 4 or less choices
add test Question | add test Question-8 | admin user makes and adds a multiple choice question with question filled and 2/4 choices filled and category | question and 2/4 answer choices and category filled | added to question bank | not added to question bank | Chrome | 2019-04-18 | fail | fix so admin can put 4 or less choices
add test Question | add test Question-9 | admin user makes and adds a multiple choice question with question filled and 2/4 choices filled and no category entered | question and 2/4 answer choices and no category filled | not added to question bank because of no category | not added to question bank because not all choices filled out | Chrome | 2019-04-18 | pass | fix so admin can put 4 or less choices
add test Question | add test Question-10 | admin user makes and adds a multiple choice question without question filled and 2/4 choices filled and category filled | no question and 2/4 answer choices and category filled | not added to question bank because of no question | not added to question bank because not all choices filled out | Chrome | 2019-04-18 | pass | fix so admin can put 4 or less choices
add test Question | add test Question-11 | admin user makes and adds a true false question with question filled and answer submited with category | question and answer with category filled. | added to question bank | added to question bank | Chrome | 2019-04-18 | pass
add test Question | add test Question-12 | admin user makes and adds a true false question with question filled and answer submited without a category | question and answer without a category | not added to question bank because of no category | addded to question bank | Chrome | 2019-04-18 | pass
add test Question | add test Question-13 | admin user makes and adds a true false question without question filled and answer submited with a category | question not filled and answers with category | not added to question bank because of no question | not added to question bank because of no question | Chrome | 2019-04-18 | pass
add test Question | add test Question-14 | admin user makes and adds a true false question with question not filled, with answer and submited without a category | question not filled with answer and no category | not added to question bank | not added to question bank | Chrome | 2019-04-18 | pass
add test Question | add test Question-15 | admin user adds question using a correctly formatted CSV file | correctly formatted CSV | questions added to question bank | questions added to question bank | Chrome | 2019-04-18 | pass
add test Question | add test Question-16 | admin user adds question using a incorrectly formatted CSV file not giving categories | incorrectly formatted CSV (missing categories) | questions without categories were not added | all questions added to question bank | Chrome | 2019-04-18 | fail | fix so that it cannot add to the question bank without a category
add test Question | add test Question-17 | admin user adds question using a incorrectly formatted CSV file not giving questions for multiple choice but giving answer choices and category | incorrectly formatted CSV (missing questions but has answer choices and categories) | questions missing the question itself are not added | questions missing the question itself were not added | Chrome | 2019-04-18 | pass
add test Question | add test Question-18 | admin user adds question using a correctly formatted CSV file with 4 or less choices for multiple choice | correctly formatted CSV with 4 or choices per multiple choice questions | questions are added to quiz bank | questions are not added to quiz bank because of less then 4 choices | Chrome | 2019-04-18 | fail | fix so admin can put 4 or less choices
Chrome
Delete question | [5 empty] | Chrome
delete question | delete question-1 | admin user deletes multiple choice question from question bank | click "x" next to desired question | question is no longer displayed in question bank and is deleted | question is no longer displayed in question bank | Chrome | 2019-04-18 | pass
delete question | delete question-2 | admin user deletes true false question from question bank | click "x" next to desired question | question is no longer displayed in question bank and is deleted | question is no longer displayed in question bank | Chrome | 2019-04-18 | pass
Chrome
Edit Question | [5 empty] | Chrome
Edit Question | Edit Question-1 | admin user clicks on edit next to a question in question bank and the proceeds to edit question and choices for multiple choice | click "edit" next to desired question | the multiple choice question, the question itself , choices and category fill up the text fields of the add question format to be readded | the multiple choice question, the question itself , choices and category fill up the text fields of the add question format to be readded | Chrome | 2019-04-18 | pass
Edit Question | Edit Question-2 | admin user clicks on edit next to a question in question bank and the proceeds to edit question and choices for true false |  | the true false question, the question itself , answer and category fill up the text fields of the add question format to be readded | the true false question, the question itself , answer and category fill up the text fields of the add question format to be readded | Chrome | 2019-04-18 | pass
Chrome
Make Test | [5 empty] | Chrome
Make Test | Make Test-1 | admin user creates a test without test name but selects questions | select questions and click create test without entering a test name | does not create test because it is not named | does create test without name and adds to Test Bank | Chrome | 2019-04-20 | fail | add a checker to check if there is a test name inputed before making the exam
Make Test | Make Test-2 | admin user creates a test without selecting questions but has a name | Test name and no questions selected | does not create test because no questions are selected | does create test without questions and adds to Test Bank | Chrome | 2019-04-20 | fail | add a checker to see if there are questions selected
Make Test | Make Test-3 | admin user creates a test without a test name and without selecting questions | no test name and no questions selected | does not create test because of no fields | does create empty exam without names and adds to Test Bank | Chrome | 2019-04-20 | fail | add checker to see if all fields are filled out
Make Test | Make Test-4 | admin user creates a test with test name and selects questions | select questions and click create test with a test name | create test and add to Test bank | create test and add to Test bank
Chrome
Delete Test | [5 empty] | Chrome
Delete Test | Delete Test-1 | Admin user deletes exam on Admin Home page | click "x" next to desired test to delete | exam is no longer displayed and deleted | exam is no longer displayed and deleted | Chrome | 2019-04-20 | pass
Chrome
Create New User's - as Admin | [5 empty] | Chrome
without admin privelages
Create New User | Create New User-1 | an admin user creates a new user with a new user name, password and retype passwords filled out and they do not have admin privlages | username: "new username", password: "new password", retype password: "new password", isAdmin: no | display on same page with list of already existing accounts | display on same page with list of already existing accounts | Chrome | 2019-04-20 | pass
Create New User | Create New User-2 | an admin user signs up with an existing user name, password and retype passwords filled out, and they do not have admin privlages and they do not have admin privlages | username: "existing username", password: "new password", retype password: "new password", isAdmin:no | alert "username already exists" | display on same page with list of already existing accounts | Chrome | 2019-04-20 | fail | add a checker to see if username exist
Create New User | Create New User-3 | an admin user signs up with an new user name, password and a differnet retype passwords filled out and they do not have admin privlages | username: "new username", password: "new password", retype password: "different password", isAdmin: no | alert "passwords do not match" | alert "passwords do not match" | Chrome | 2019-04-20 | pass
Create New User | Create New User-4 | an admin user signs up with an new user name, an existing password and a retype passwords filled out and they do not have admin privlages | username: "new username", password: "existing password", retype password: "existing password", isAdmin: no | alert "password already in use" | display on same page with list of already existing accounts | Chrome | 2019-04-20 | fail | add a checker to see if password is already being used
Create New User | Create New User-5 | an admin user signs up with an existing user name, an existing password and a retype passwords filled and has no admin privelages | username: "existing username", password: "existing password", retype password: "existing password", isAdmin: no | alert "username and password already in use" | display on same page with list of already existing accounts | Chrome | 2019-04-20 | fail
with admin privelages
Create New User | Create New User-6 | an admin user creates a new user with a new user name, password and retype passwords filled out and they do have admin privlages | username: "new username", password: "new password", retype password: "new password", isAdmin: yes | display on same page with list of already existing accounts | display on same page with list of already existing accounts | Chrome | 2019-04-20 | pass
Create New User | Create New User-7 | an admin user signs up with an existing user name, password and retype passwords filled out, and they do have admin privlages | username: "existing username", password: "new password", retype password: "new password", isAdmin: yes | alert "username already exists" | display on same page with list of already existing accounts | Chrome | 2019-04-20 | fail | add a checker to see if username exist
Create New User | Create New User-8 | an admin user signs up with an new user name, password and a differnet retype passwords filled out and they do have admin privlages | username: "new username", password: "new password", retype password: "different password", isAdmin: yes | alert "passwords do not match" | alert "passwords do not match" | Chrome | 2019-04-20 | pass
Create New User | Create New User-9 | an admin user signs up with an new user name, an existing password and a retype passwords filled out and they do have admin privlages | username: "new username", password: "existing password", retype password: "existing password", isAdmin: yes | alert "password already in use" | display on same page with list of already existing accounts | Chrome | 2019-04-20 | fail | add a checker to see if password is already being used
Create New User | Create New User-10 | an admin user signs up with an existing user name, an existing password and a retype passwords filled and has admin privelages | username: "existing username", password: "existing password", retype password: "existing password", isAdmin: yes | alert "username and password already in use" | display on same page with list of already existing accounts | Chrome | 2019-04-20 | fail
View Test Users results as admin
View Test Users | View Test Users-1 | an admin user clicks on a users result for a test they took and views there test results: questions, they're answer choice and the correct answer choice | click on the test in the users list of completed exams under there name | redirect to the test result page of that test user with their anwer choices and correct answer | redirect to the test result page of that test user with their anwer choices and correct answer | Chrome | 2019-04-25 | pass